## Project Plan
Sprint | Feature | Story | Story Points | Subtasks
Sprint 1 | Homepage | Design homepage | 5 | Wireframes, HTML/CSS layout, Animations, User Testing
Sprint 1 | Homepage | Add Agile introduction | 3 | Write content, Format for web
Sprint 1 | Homepage | Include navigation links | 2 | Develop navbar, Link pages
Sprint 2 | Agile Values | Page for Agile values | 5 | Display values, Add brief descriptions
Sprint 2 | Agile Values | Interactive principles | 8 | Interactive visualizations, Examples
Sprint 2 | Agile Values | Add illustrative examples | 8 | Real-world examples, Editable templates
Sprint 3 | Resource Library | Library design | 5 | Create library UI, Backend API setup
Sprint 3 | Resource Library | Downloadable resources | 3 | Add downloadable templates, Guides
Sprint 3 | Resource Library | Search and filter functionality | 5 | Search bar functionality, Filters for content
Sprint 4 | Collaboration Features | Discussion forum | 8 | Forum UI, Backend for posts, Testing
Sprint 4 | Collaboration Features | Enable comments | 8 | Comment input field, Store comments in DB, API integration
Sprint 4 | Collaboration Features | User authentication | 5 | User signup/login, Session management, Testing